## Schedule
CardioSaarthi - Project Schedule
Sixteen weeks ¦ Semester VII, 2026-27 ¦ AI-ECG Tutor System
Project start (Monday of week 1) |  | 2026-07-20 |  | Yellow cells are inputs. Edit Start/End week and the bars move.
Today |  | 2026-08-16
Current week |  | 4
Phase | Task | Start wk | End wk | Weeks | Status | Start date | End date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Phase 1 | Dataset acquisition & quality screening | 1 | 1 | 1 | Done | 2026-07-20 | 2026-07-26
Phase 1 | Measurement engine (detection, delineation, intervals) | 1 | 3 | 3 | Done | 2026-07-20 | 2026-08-09
Phase 1 | Standards-compliant ECG rendering | 2 | 3 | 2 | Done | 2026-07-27 | 2026-08-09
Phase 1 | Technical validation vs LUDB & QTDB | 3 | 3 | 1 | Done | 2026-08-03 | 2026-08-09
Phase 1 | Clinical scenario generation (offline LLM batch) | 4 | 5 | 2 | Not started | 2026-08-10 | 2026-08-23
Phase 1 | Faculty review interface | 4 | 5 | 2 | Not started | 2026-08-10 | 2026-08-23
Phase 1 | Faculty review cycles -> approved case bank | 5 | 8 | 4 | Not started | 2026-08-17 | 2026-09-13
Phase 2 | Session state machine & step-lock orchestration | 7 | 7 | 1 | Not started | 2026-08-31 | 2026-09-06
Phase 2 | Deterministic grading + error taxonomy | 7 | 8 | 2 | Not started | 2026-08-31 | 2026-09-13
Phase 2 | Knowledge base ingestion & embeddings (pgvector) | 8 | 8 | 1 | Not started | 2026-09-07 | 2026-09-13
Phase 2 | Student interface - nine-step case player | 8 | 10 | 3 | Not started | 2026-09-07 | 2026-09-27
Phase 2 | Competency model & spaced repetition | 9 | 10 | 2 | Not started | 2026-09-14 | 2026-09-27
Phase 3 | LLM wrapper + CardioSaarthi persona configuration | 9 | 9 | 1 | Not started | 2026-09-14 | 2026-09-20
Phase 3 | RAG retrieval & citation pipeline | 9 | 10 | 2 | Not started | 2026-09-14 | 2026-09-27
Phase 3 | Output validation, fallback library, caching | 10 | 11 | 2 | Not started | 2026-09-21 | 2026-10-04
Phase 3 | Persona fixture suite (40 error scenarios) | 11 | 11 | 1 | Not started | 2026-09-28 | 2026-10-04
Phase 3 | Patient report explainer | 12 | 13 | 2 | Not started | 2026-10-05 | 2026-10-18
Phase 4 | Faculty analytics console | 11 | 12 | 2 | Not started | 2026-09-28 | 2026-10-11
Phase 4 | Technical validation report (final) | 13 | 13 | 1 | Not started | 2026-10-12 | 2026-10-18
Phase 4 | Study setup - ethics, consent, cohort scheduling | 12 | 14 | 3 | Not started | 2026-10-05 | 2026-10-25
Phase 4 | Pre-test / post-test with nursing cohort | 14 | 15 | 2 | Not started | 2026-10-19 | 2026-11-01
Phase 4 | Analysis, documentation & final report | 15 | 16 | 2 | Not started | 2026-10-26 | 2026-11-08
PHASE SUMMARY
Phase | Start wk | End wk | Tasks | Done | Complete
Phase 1 | 1 | 8 | 7 | 4 | 57.14%
Phase 2 | 7 | 10 | 5 | 0 | 0%
Phase 3 | 9 | 13 | 5 | 0 | 0%
Phase 4 | 11 | 16 | 5 | 0 | 0%
Critical path: faculty review throughput in weeks 5-8, not engineering.

## Milestones
Milestones
Week | Milestone | Status | Date
3 | Engine validated against LUDB & QTDB | Done | 2026-08-09
4 | First faculty review session | Planned | 2026-08-16
8 | 60 approved cases in the bank | Planned | 2026-09-13
10 | Student runtime live end to end | Planned | 2026-09-27
13 | Layers 3 and 4 complete | Planned | 2026-10-18
16 | Final submission | Planned | 2026-11-08
Formulas:
Date = Schedule!$C4+[Week]*7-1

## Read me
CardioSaarthi - Project Schedule
How to edit
Yellow cells are the only ones to type in:
Schedule!C4 project start date (Monday of week 1)
Start wk / End wk week numbers for each task
Status Done / In progress / Not started (dropdown)
Everything else is a formula. The Gantt bars are conditional formatting
driven by Start wk and End wk, so editing a week number moves the bar
immediately - there is no chart to redraw and no colour to repaint.
Marking a task Done turns its bar from pale to solid.
Colour
Solid bar delivered and validated
Pale bar planned
Phase colours match the methodology diagram, so the slides read as one system.
Status at end of week 3
Phase 1 is 4 of 7 tasks complete. The measurement engine, the renderer and
the technical validation are delivered. The case bank is not, because a case
bank is not finished until faculty have approved it.
Critical path
Faculty review throughput in weeks 5-8, and study setup in weeks 12-14.
Neither is a coding task. Both should be booked in advance rather than
requested when needed.